## Lead
Housekeeper Scheduling System
Group Number - 5
Date:- 11th April To 16th April
Team Lead & Frontend Lead- Puja Ganesh Devkar
Backend Lead-Rajeshwari M Shettar

## Status Meeting
Status Meeting 216 Java SL SG Group - 5
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-04-11 | 9am | Database Schema | 2pm | Tables,PK | 6pm | Everyone
2022-04-12 | 9am | Front-End | 2pm | Angular | 6pm | Frontend-Team
2022-04-13 | 9am | Front-End | 2pm | Angular | 6pm | Frontend-Team
2022-04-14 | 9am | Server-Side | 2pm | Spring Boot | 6pm | Frontend-Team
2022-04-15 | 9am | Back-End | 2pm | MySQL Database | 6pm | Backend-Team
2022-04-16 | 9am | Back-End | 2pm | Unit Testing | 6pm | Backend-Team

## Status Track
Project Status Check Report Team - 216 Java SL SG - Group-5
Sr.No. | Employee ID | Name | Domain | Module | 11th April-22 | 12th April-22 | 13th April-22 | 14th April-22 | 15th April-22 | 16th April-22
1 | 2492201 | Pooja X | Front End | Phase-2 | Student Login | Student Login | Student Registration | Student Registration | Code Collaboration | Project Completion
2 | 2491188 | Prateek Srivastava | Front End | Phase-2 | About Us | About Us | Contact Form | Project Documentation | Code Collaboration | Project Completion
3 | 2491498 | Pravinkumar M | Back End | Phase-3 | Controllers Modules | Controllers Modules | Controllers Modules | Controllers Modules | Code Collaboration | Project Completion
4 | 2492348 | Prince Kumar | Back End | Phase-1 | Database Design | Database Tables | JDBC Hibernate | Application Properties | Integration with Front End | Project Completion
5 | 2492276 | Prtiksha Shankar Kashid | Front End | Phase-2 | Housekeeper Services | Housekeeper Services | Housekeeper Services | Housekeeper Services | Code Collaboration | Project Completion
6 | 2492421 | Puja Ganesh Devkar | Front End | Phase-2 | Admin Login | Admin Registration | Housekeeper Login | Housekeeper Registration | Code Collaboration | Project Completion
7 | 2492625 | Rahul Adaki | Back End | Phase-3 | Repository Modules | Repository Modules | Repository Modules | Repository Modules | Code Collaboration | Project Completion
8 | 2490232 | Rajeshwari M Shettar | Back End | Phase-3 | Service Modules | Service Modules | Service Modules | Service Modules | Code Collaboration | Project Completion
9 | 2491830 | Ranjithkumar X | Back End | Phase-3 | Models Modules | Models Modules | Models Modules | Models Modules | Code Collaboration | Project Completion
10 | 2492123 | Rishikesh Rajendra Kulkarni | Front End | Phase-4 | Front End CSS Styling | Front End CSS Styling | Backend Unit Testing | Frontend Unit Testing | Testing Report | Project Completion